IIT GANDHINAGAR • WEEK 1, DAY 5 PM • POST-AGILE TEACHING BLOCK Agile in Action From Chaos to Clarity A contrast-based exercise — do the same task without Agile, then with it. Feel the difference.

## EXERCISE OVERVIEW

| Type | Guided → Semi-Guided Mix |
| --- | --- |
| Duration | ~75 minutes (fits in 2:00–3:30 PM practical block) |
| Group Size | Individual (Parts 1-3) → Groups of 4 (Part 4) |
| Materials | Paper/notebook, this handout, pen |
| Interview Relevance | Every L4+ PM/engineering interview asks 'How do you plan and track work?' |

How This Exercise Works

You'll do the same tasks twice — first without structure, then with Agile. The contrast is the lesson.

| Part | What You Do | Time | Mode |
| --- | --- | --- | --- |
| 1 | The Chaos Round — plan a project with zero structure | 10 min | Guided (individual) |
| 2 | The Agile Round — plan the SAME project using Agile | 15 min | Guided → Semi-Guided |
| 3 | Standup Showdown — give updates bad way vs BLUF way | 15 min | Guided → Practice |
| 4 | AI Mission Brief — full Agile planning for AI project | 25 min | Semi-Guided (groups) |
| 5 | Debrief — reflection + key takeaways | 10 min | Guided (cohort) |

PART 1 THE CHAOS ROUND 10 minutes • Guided — Individual

The Scenario

Your team has been asked to build an AI-powered campus food ordering system for IIT Gandhinagar. The mess committee wants students to:

▸  See the day's menu on their phone before meals

▸  Pre-order special items (limited quantity, first-come-first-served)

▸  Rate meals and give feedback (1-5 stars + comment)

▸  Get AI-suggested meals based on dietary preferences and past ratings

Timeline: 2 weeks to build and deploy.

Your Task (5 minutes — work alone, no templates)

On this page, answer these 4 questions. No frameworks, no structure. Just write whatever comes to mind.

1. What will you build? (describe the app in your own words)

An app that shows the options directly on the home screen, reducing complexity and increasing usability. The menu options will be updated from the admin side every day, but they can also set a routine of meals that can be automatically shown. For example, for the month of February, the menu will update automatically every day. The admin can also add meals for a week which would repeat throughout the month. They can add the status of the food every day or specify if it is limited and first-come-first-served. That way, students can see that it is limited and go to the pre-order icon and then pre-order it, which can be sent to the admin side to know how much quantity needs to be prepared. Students have the feature to rate the meal for the whole day, and it resets every day. They can choose which meal to rate and then have the criteria they want to rate on. They can also add comments while rating. This way, they don’t have to rate the meal immediately if it is not possible at that time. With the GenAI feature, every student can give context about their dietary restrictions, and that way GenAI can suggest food by looking at that and using past ratings to rank the food.

2. How will you split the work across your team?

The app will require student users and admin users. First, the client and the team will interact to understand any constraints or specific features they require. Then a PRD will be drafted, which will be shared with the design team for UI/UX and with the web developer to create an MVP. I will assign tasks according to the required skills. I will split the work into design, frontend (user side), admin side, and backend for storage.

3. When will each part be done?

Design will be completed within a week so that frontend, user, and admin development can work accordingly, and concurrently the backend will also be working. For the MVP, frontend and backend will be done within two weeks. Then we can present it to the client and hold a conversation about the app and improvements they require. That way, the client can see it and not have only a theoretical idea.

4. How will you know if you're on track?

We will know if we are on track if the MVP is created within two week

🔍 CHECKPOINT — What the Trainer Will Surface After 3-4 students read their plans aloud, watch for these patterns (they WILL appear): ▸ "We'll build the whole thing first, then test" → Waterfall disguised as a plan ▸ "I'll do frontend, you do backend" → No shared understanding of scope ▸ "Should take about 2 weeks" → Pure guessing, no estimation methodology ▸ No mention of user feedback → Who validates you're building the right thing? ▸ Vague deliverables like "make the app" → What does "done" even mean? Key Takeaway: Every plan you just wrote is a waterfall plan in disguise.

PART 2 THE AGILE ROUND 15 minutes • Guided → Semi-Guided

Same project. Same 2 weeks. Same team. Now with Agile structure.

Step 1 — Write User Stories

Trainer demos this one: "As a student, I want to see today's menu on my phone before breakfast so that I can decide whether to eat at the mess or go outside." → 3 story points

Now you write 5 more. Use the exact format. Be specific — no vague stories.

Story Points Quick Reference 1 pt = Trivial (under 1 hour) → e.g., add a footer to the app 2 pts = Simple, clear path → e.g., display a static menu page 3 pts = Moderate, some decisions → e.g., meal rating system (stars + comment) 5 pts = Complex, multiple components → e.g., pre-order system with quantity limits 8 pts = Hard, significant unknowns → e.g., AI meal recommendations from past ratings

| # | User Story | Points |
| --- | --- | --- |
| 1 | As a student, I want to see today's menu on my phone before breakfast so that I can decide whether to eat at the mess or go outside. | 3 |
| 2 | As a _STUDENT_, I want to _PREORDER LIMITED ITEMS_ so that _I DON’T MISS OUT ON THEM__. | 5 |
| 3 | As a _STUDENT________________, I want to _RATE THE FOOD I AM EATING AT THE MESS________________ so that __I CAN GIVE FEEDBACK FOR IMPROVEMENTS____. | 3 |
| 4 | As a __STUDENT_______________, I want to ___BE ABLE TO KNOW WHAT FOOD TO EAT______________ so that __I HAVE THE BEST-TASTING/HIGHEST QUALTIY OF FOOD_______________. | 8 |
| 5 | As a __STUDENT_________, I want to __BE ABLE TO LOGIN MY DETIALS AND HAVE A PERSONALIZED PROFILE______________ so that __I CAN SEE MY RATING HISTORY____________. | 2 |
| 6 | As a ____ADMIN_____________, I want to ____SEE THE COMPILATION ALL RATING AND FEEDBACK _____________ so that ___I CAN LOOK AT THE KEY AREAS TO IMRPOVE______________. | 3 |

Step 2 — Sprint Planning

You have 2 weeks = 2 sprints. Assign your stories to sprints. Sprint 1 capacity ≤ 15 points (unknown velocity — start conservative).

SPRINT 1 (Week 1)  —  Goal: __MEAL RATING AND AL MEAL RECOMMENDATION SYSTEM______________________________________

| Story # | User Story (short version) | Points | Owner |
| --- | --- | --- | --- |
| 3 | MEAL RATING SYSTEM | 3 | FRONTEND |
| 4 | AI RECOMMENDATION SYSTEM | 8 | AI ENGINEER |
| TOTAL |  | _11_ / 15 |  |

SPRINT 2 (Week 2)  —  Goal: ___CREATE _____________________________________

| Story # | User Story (short version) | Points | Owner |
| --- | --- | --- | --- |
| 1 | MENU PAGE | 3 | FRONTEND DESIGNER |
| 5 | USER SPECIFIC PROFILE | 2 | BACKEND |
| 2 | PRE ORDERING SYSTEM | 5 | ML ENGINEER |
| 6 | IMPROVEMENT AREA SYSTEM | 3 | ML ENGINEER |
| TOTAL |  | _13_ / 15 |  |

Step 3 — Compare Your Two Plans

Look at your Chaos Round plan (Part 1) and your Agile plan (Part 2) side by side. Answer honestly.

| Question | Chaos Round | Agile Round |
| --- | --- | --- |
| Can you tell what 'done' looks like for Week 1? | NO | YES |
| Could a new team member join and understand the plan? | YES, BUT THEY WOULD HAVE TO GO TO EACH MEMBER INDIVIDUALLY | YES |
| When does the mess committee first SEE something working? | WEEK 2 | WEEK 2 |
| If you fall behind by Day 3, how quickly would you know? | NOT QUICKLY ENOUGH | BY THE END OF DAY 3 |
| Can you identify the riskiest part of the project? | ORGANIZED BUT NOT OPTIMIZED | ORGANIZED AND OPTIMIZED |

The Difference Should Be Obvious One plan is a wish. The other is a system. Agile doesn't add more work — it adds more CLARITY about what the work actually is.

PART 3 THE STANDUP SHOWDOWN 15 minutes • Guided → Live Practice

Round A — The Bad Standup (Trainer reads aloud)

The Bad Update (read this in a mumbling, vague tone) "Yeah so... I've been working on the project. It's going okay I think. I did some stuff with the menu page. I'll keep working on it. No blockers."

What's wrong with this? (call out the problems as a class)

| Problem | Why It's Bad |
| --- | --- |
| No specifics | What "stuff"? What menu page? Which part of it? |
| No evidence | No commit, no screenshot, no test resultDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDDD |
| "I think" | You don't actually know your own status |
| "Keep working on it" | No plan for today — just vibes |
| "No blockers" | Either lying or hasn't thought about it |

Round B — Rewrite It Using BLUF (3 min — individual)

Same scenario: It's Wednesday of Sprint 1. You've been working on the food ordering app for 3 days. Rewrite the update properly.

OPENING (10 sec) Yesterday I completed: What was the specific task? What's the evidence (commit hash, screenshot, test passing)?

Yesterday, I completed the initial logic for the AI-based meal recommendation model using user dietary preferences and past ratings.

DETAIL (20 sec) Specifically, I: What exactly did you do? Name the files, the functions, the feature.

I implemented a ranking algorithm that filters meals based on dietary constraints and assigns weighted scores using past rating averages. The function generateRecommendations() is implemented in recommendation.py. I tested it using mock user data and verified that vegetarian users are only shown vegetarian meals.

TODAY (15 sec) Today I'm working on: What specific task? Expected output? By when?

Today, I am integrating this logic with the backend endpoint GET /recommendations so that it can dynamically fetch user history from the database. Expected completion is by end of day.

BLOCKER (15 sec) I'm blocked on: What's the problem? What have you tried? What do you need from someone?

I need final confirmation on how dietary preferences are stored in the user profile schema. Currently, I am assuming a JSON field, but I need schema validation from the database engineer.

Round C — Live Practice (Groups of 4 — 8 min)

1.  Form groups of 4 (closest neighbors) — STAND UP

2.  Each person delivers their BLUF update from Round B

3.  TIMER: 90 seconds per person. Timekeeper CUTS YOU OFF at 90.

4.  After all 4 go → group picks: Who gave the clearest update? Why?

5.  3 volunteers deliver to the full cohort (1 min each)

| Criteria | What to Look For |
| --- | --- |
| Specificity | Did they name exact tasks — not vague 'stuff'? |
| Evidence | Did they mention a commit, screenshot, or test result? |
| Time awareness | Did they estimate when today's work would be done? |
| Honest blockers | Did they ask for help — or claim 'no blockers' dishonestly? |
| BLUF structure | Did they lead with the main point, not bury it? |
| Delivery | Eye contact, clear voice, no filler words, under 90 sec? |

PART 4 AI MISSION BRIEF 25 minutes • Semi-Guided — Groups of 4

This is where it all comes together. A realistic AI project — plan it end-to-end using Agile.

CLIENT BRIEF Client: A mid-size EdTech company with 500 students across 3 cohorts. Problem: Students submit assignments via email, Google Forms, and WhatsApp — no single system. Faculty waste 6+ hours/week hunting for submissions. Late submissions slip through. Students game the system ("I sent it but it didn't reach you"). Build an AI-Powered Assignment Submission & Tracking System that: ▸ Accepts submissions via a single web portal ▸ Auto-validates: correct file format, file size, naming convention ▸ Timestamps every submission (tamper-proof) ▸ Uses an LLM to auto-generate a 2-line summary of each submission ▸ Flags potential plagiarism by comparing similarity across submissions ▸ Sends automated reminders 2 hours before deadline ▸ Provides a faculty dashboard showing submission status per student Constraints: 4 engineers • 3 sprints of 1 week each • Python + any LLM API + any DB • Must deploy (not localhost)

## DELIVERABLE 1 — User Stories (Write at least 8)

| # | User Story | Pts | Priority |
| --- | --- | --- | --- |
| 1 | As a student, I want to upload my assignment through a web portal so that my submission is officially recorded. | 5 | Must |
| 2 | As a system, I want to validate file format, file size, and naming conventions so that only correct submissions are accepted. | 5 |  |
| 3 | As a student, I want a tamper-proof timestamp generated automatically upon submission so that deadlines are enforced fairly. | 3 |  |
| 4 | As a faculty member, I want to see a dashboard of all students and their submission status so that I can track who has submitted and who has not. | 5 |  |
| 5 | As a faculty member, I want automatic reminders sent to students two hours before the deadline so that late submissions are reduced.. | 3 | SHOULD |
| 6 | As a system, I want to generate a two-line AI summary of each assignment so that faculty can quickly understand the content. | 8 | SHOULD |
| 7 | As a faculty member, I want plagiarism similarity scores across submissions so that potential copying is flagged. | 8 | COULD |
| 8 | As a student, I want to see confirmation after submission so that I know my file was successfully uploaded. | 2 | MUST |

Priority Guide Must = Without this, the system is useless (e.g., file upload, timestamp) Should = Important but system works without it (e.g., LLM summaries) Could = Nice-to-have, cut first if behind (e.g., plagiarism detection)

## DELIVERABLE 2 — Sprint Plan

Your team velocity for Sprint 1 = ~20 story points (4 people × 5 pts each, conservative). Don't overcommit.

SPRINT 1  —  Goal: __Students can successfully upload assignments with validation and Timestamp______________________________

(What is the ONE thing that must work by end of this sprint?)

| Story # | Short Description | Pts | Owner | Definition of Done |
| --- | --- | --- | --- | --- |
| 1 | File upload Portal | 5 | Frontend | Students can upload files via portal and receive confirmation |
| 2 | File Validation Logic | 5 | Backend | Invalid files are rejected with proper error messages |
| 3 | Timestamp System | 3 | Database Engineer | Timestamp auto-generated and stored securely |
| 8 | Submission Confirmation | 2 | Frontend | Success message displayed and stored |
| 4 | Basic faculty Dashboard | 5 | Frontend | Faculty can see submission list per assignment |
| TOTAL |  | _20_/20 |  |  |

SPRINT 2  —  Goal: __Automate reminders and integrate AI summaries_____________________________________________

(What is the ONE thing that must work by end of this sprint?)

| Story # | Short Description | Pts | Owner | Definition of Done |
| --- | --- | --- | --- | --- |
| 5 | Automated Reminder System | 3 | Backend | Email reminders trigger 2 hours before deadline |
| 6 | LLM Summary Integration | 8 | Ai Engineer | Summary generated and stored per submission |
| 4 | Dashboard Enhancement | 5 | Frontend | Dashboard shows timestamp and summary |
|  | Refactoring and Deployment Hardening | 4 | DevOps | System deployed on cloud with monitoring |
| TOTAL |  | _20_/25 |  |  |

SPRINT 3  —  Goal: ___Plagiarism detection and system optimization_______________________________________

(What is the ONE thing that must work by end of this sprint?)

| Story # | Short Description | Pts | Owner | Definition of Done |
| --- | --- | --- | --- | --- |
| 7 | Plagiarism Similarity Engine | 8 | Al Engineer | Similarity score generated for each submission pair |
|  | Similarity Display in Dashboard | 5 | Frontend | Faculty can see flagged submission |
|  | Bulk Upload Handling Optimization | 5 | Backend | System handles 500 submissions within acceptable latency |
|  | Secure File Storage | 5 | DevOps | Files stored securely with access control |
| TOTAL |  | _23_/25 |  |  |

## DELIVERABLE 3 — Risk Register

What could go wrong? Identify at least 4 risks. Two are pre-filled as examples.

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| LLM API rate limits hit during bulk submission period | H | H | Implement caching and batch processing, monitor API usage |
| Plagiarism detection has too many false positives | M | M | Tune similarity threshold and allow manual override |
| Cloud deployment misconfiguration | M | H | Use staging environment and CI/CD pipeline |
| Deadline-based reminder service fails | L | H | Add background job monitoring and logging |
| File storage overflow | M | M | Implement size limits and archive old submissions |

## DELIVERABLE 4 — Day 3 Standup Role-Play

It's Day 3 of Sprint 1. Each team member picks a role and writes a realistic standup update. Then deliver it to your group — standing up, 90 seconds, timed.

ENGINEER A — Backend / API Focuses on: file upload endpoint, validation logic, database schema

Yesterday I completed: completed the POST /upload endpoint with validation logic for file type and size.

Evidence (commit / screenshot / test): Commit hash a05v7j04 pushed to main branch. Postman tests passed for valid and invalid file formats.

Today I'm working on: I am implementing database schema finalization and linking uploads with student IDs.

Expected done by: Expected done by 6 PM.

Blocker (if any): Need confirmation from frontend on file metadata fields required in API response

ENGINEER B — LLM Integration Focuses on: submission summary generation, prompt engineering, API calls

Yesterday I completed: Integrated the LLM API for generating summaries and tested it on 10 mock assignment files.

Evidence (commit / screenshot / test): Screenshot of generated summaries and successful API responses logged in console.

Today I'm working on: I am building the faculty dashboard table with submission status indicators.

Expected done by: Expected done by end of day.

Blocker (if any): Need clarity on color coding system for late submissions.

ENGINEER C — Database / Deployment Focuses on: database setup, deployment pipeline, timestamp system

Yesterday I completed: Yesterday I set up PostgreSQL schema and configured secure timestamp storage

Evidence (commit / screenshot / test): Migration script committed and tested in staging.

Today I'm working on: Today I am configuring deployment on AWS with automated environment variables.

Expected done by: Expected done by 7 PM.

Blocker (if any): Need IAM role confirmation for file storage access permissions.

ENGINEER D — Frontend / Dashboard Focuses on: student upload page, faculty dashboard, status indicators

Yesterday I completed: Yesterday I completed the basic student upload UI and connected it to the backend endpoint.

Evidence (commit / screenshot / test): UI working in staging with successful upload confirmation.

Today I'm working on: Today I am building the faculty dashboard table with submission status indicators.

Expected done by: Expected done by end of day.

Blocker (if any): Need clarity on color coding system for late submissions.

## DELIVERABLE 5 — Sprint 1 Review Script

It's the end of Sprint 1. Write your demo script — what do you show the client?

COMMITMENT: "Here's what we committed to this sprint:" List your sprint goal + the stories you planned

Our Sprint 1 goal was to enable secure assignment submission with validation and timestamping. We committed to file upload, validation logic, timestamp storage, submission confirmation, and a basic faculty dashboard.

REALITY: "Here's what we actually delivered:" Be honest — what's DONE vs what didn't make it?

All planned stories were completed except minor UI polish on the dashboard filters.

LIVE DEMO: "Let me show you it working:" What would you show running? Be specific.

We will show the student uploading an assignment, validation rejection for incorrect file format, automatic timestamp generation, and faculty dashboard reflecting submission status in real time.

LEARNINGS: "What we learned / What changed:" Scope adjustments? Technical discoveries? Estimate corrections?

File parsing for large PDFs was slower than expected. We optimized backend file handling and adjusted estimation for future AI-related tasks.

NEXT SPRINT: "Sprint 2 preview:" What's next? Any re-prioritization needed?

We will focus on AI summaries and automated reminders. Plagiarism detection will begin in Sprint 3.

PART 5 DEBRIEF + FAST FINISHER STRETCH 10 minutes • Guided — Cohort

Personal Reflection (2 min — write silently)

1. What was the single biggest difference between planning without Agile and planning with it?

Planning with Agile gave specific tasks with the understanding of why we are making them. In the normal way, we had tasks but without understanding their requirements.

2. What's the ONE thing about standups that will be hardest for you personally? Why?

Identifying specific blockers in different situations will be the hardest part for me.

3. Starting tomorrow — what specific Agile behavior will you adopt for Project AdmitGuard?

For any improvement in the project, I will create user stories and then divide the work accordingly.

FAST FINISHER STRETCH — The Curveball

SCOPE CHANGE (For groups that finish Part 4 early) You're 2 days into Sprint 2. The client walks in and says: "We just realized we also need the system to work with WhatsApp submissions — some faculty refuse to stop using WhatsApp. Can you add a WhatsApp bot that accepts submissions via message?" This is a scope change mid-sprint. What do you do?

| Strategy | What You'd Say to the Client |
| --- | --- |
| NEGOTIATE | "We can add it, but something else moves out of Sprint 2. Which current feature is lower priority?" |
| DEFER | "We'll add it to the backlog and plan it for Sprint 3. Here's why: [reason]." |
| SPIKE | "We'll do a 2-hour investigation to check feasibility, then give you an honest estimate." |
| ACCEPT (rarely right) | "We'll absorb it." — Only if team has slack AND it's truly critical. |

Your team's response:

Strategy chosen: SPIKE

What we'd say to the client (exact words): This is a valuable requirement. Before committing, we suggest conducting a short two-hour technical investigation to evaluate WhatsApp API integration, webhook handling, authentication, and file transfer limitations. Once we complete this investigation, we will provide an accurate effort estimate and recommend whether it fits into Sprint 2 or should be scheduled for Sprint 3.

Why this strategy (what are we optimizing for?): We are optimizing for technical certainty before making delivery commitments. A spike reduces ambiguity and prevents inaccurate estimation.

The Real Skill The skill isn't saying 'yes' or 'no' — it's saying 'yes, AND here's the tradeoff.' This is one of the most common real-world situations in Agile teams. Interviewers at Amazon, Google, and Uber specifically test for this.

## SCORING RUBRIC

This exercise contributes to today's session participation (Labs & GitHub WPS component).

| Criteria | Points | What's Assessed |
| --- | --- | --- |
| User Stories quality | 30 | Specific? INVEST criteria met? Story points reasonable? |
| Sprint Plan completeness | 25 | Goals clear? Points within velocity? Definition of Done stated? |
| Standup quality (live) | 25 | BLUF format? Specific? Under 90 sec? Evidence mentioned? |
| Risk Register + Scope | 10 | Realistic risks? Thoughtful mitigation? Curveball handled well? |
| Participation | 10 | Spoke up in group? Explained reasoning? Engaged in sprint review? |

What Happens Next ✓ Daily standups start at 5:30 PM today — use the BLUF format from Part 3 ✓ Saturday's Project AdmitGuard showcase = your first Sprint Review ✓ Fill the standup prep template BEFORE every standup for the next 19 weeks ✓ By Week 18, you'll have done 100+ standups — that's 100 reps of a skill most candidates fake ✓ When an interviewer asks 'How do you plan work?' — you'll answer from experience, not a textbook

IIT Gandhinagar  •  PG Diploma in AI-ML & Agentic AI Engineering  •  Week 1 Day 5